## Slide 1: Project Overview
Ernesto Damiani, Angela Miola
Kick-off meeting
Milan, January 21, 2016
Toreador TrustwOrthy model-awaRE Analytics Data platfORm

## Slide 2: Presentation outline
Project overview and changes to project structure
Governance
Reporting
Personnel costs
Contact details

## Slide 3: Project overview
Duration: from January 1st, 2016 to December 31st, 2018
10 Partners
5 Work Package Areas
16 Work Packages
85 Deliverables
3 Milestones
2 Reviews

## Slide 4: Project Areas
Work Package Areas (WPA)
WPA1: Big Data models
WPA2: Model-based Big Data Analytics as a Service
WPA3: Architecture and toolkit
WPA4: Pilot, exploitation, and innovation
WPA5: Project management

## Slide 5: Project structure
WP and Deliverables were renumbered!
EC Commission does not allow two-level numbering of WPs (“WP 1.1” etc. as originally written in the proposal)
So:
  WP 1.1 becomes WP 1
  WP 1.2 becomes WP 2
  Deliverable 1.1.1 becomes Deliverable 1.1
  Deliverable 1.1.2 becomes Deliverable 1.2
  Etc.

## Slide 6: Milestones
M1 (month 12) “Requirements, models, and initial set of TOREADOR MBDAaaS components and toolkits”
M2 (month 24) “Integrated prototype implementation, pilot deployment, and advanced TOREADOR MBDAaaS components and toolkits”
M3 (month 36) “Integrated framework and final validation based on pilots”

## Slide 7: Documents
New in Horizon 2020
  No DoW (Document of Work) for Horizon 2020 projects
  DoA (Document of Actions) is excerpt of proposal Part B

## Slide 8: Governance
The Project Coordination Committee (PCC)
The Project Coordinator (PCO)
The Scientific and Technical Committee (STC) including Innovation Manager (IM)
The Scientific-Technical Coordinator (STCO)
The Project Office (PO)
Advisory Board (AB), including two workgroups of experts
  Specialist workgroup
  SME focus workgroup
Advisory Board Chair (ABC)

## Slide 9: Governance: management structure
Commission
TOREADOR
project
PCC
PCO
STC
STCO
AB
ABC
PO

## Slide 10: Project Coordination Committee (PCC)
Highest decision body
Responsibilities: in charge of all contractual matters including
  Legal, ethical and financial matters (e.g. adjustments)
  Consortium constitution structure and resolution of IPR issues.
One representative of each partner in the consortium
  He/she will have the legal authority to take decisions that commit the organization
Chaired by the PCO (Project Coordinator)

## Slide 11: Project Coordination Committee (PCC)
This committee meets
  Once per year, or
  When matters that require its attention arise
Extraordinary meetings will be called by PCO or when two or more partners in consortium formally request a PCC
PCO has responsibility for
  Organization of the PCC meetings
  Timely distribution of the agenda including matters for voting
PCC meetings will be held either physically or electronically

## Slide 12: Project Coordinator (PCO)
Overall responsibility for the organization, coordination, planning, communication and control of the project
Responsibility for communication between the consortium and the European Commission
Special duty of ensuring the timely delivery of the deliverables, financial reports and any other contractually relevant document to the Commission
Responsibility for communicating the views of the Commission and external stakeholders (including project reviewers and AB members) to the consortium

## Slide 13: PCC members
One representative from each partner in the consortium + PCO
PCO (Project Coordinator): Damiani (CINI)
CINI: Malerba
ENG:
SAP:
CITY:
LIGHT:
TAIGER:
ATOS:
B&B:
DTA:
JOT:

## Slide 14: Scientific & Technical Committee (STC)
Highest technical management body
Responsibilities
  Overseeing and ensuring the technical integration of project results
  Identifying cross-cutting technical problems
  Dealing with emerging research and technical issues
  Dealing with innovation management and assessing the ongoing scientific & technological developments
STC includes:
  The STCO (Scientific-Technical Coordinator)
  The leaders of all the work packages of the project
Chaired by the STCO

## Slide 15: Scientific & Technical Committee (STC)
  STC will meet at least three times per year
    Scientific-technical evaluation
  Extraordinary meetings when required by project partners
  STC meetings will be held either physically or electronically

## Slide 16: Scientific & Technical Coordinator (STCO)
  The STCO will chair the STC
  Responsibility for coordinating all technical activities of TOREADOR
  The STCO is appointed at the kick-off meeting

## Slide 17: STC members
STC includes STCO plus one from each WP leader
STCO (Scientific-Technical Coordinator) : Damiani (CINI)
CINI (WP1 WP2 WP3 WP13 WP14): Malerba (CINI)
SAP (WP6 WP9)
CITY (WP4)
LIGHT (WP10)
TAIGER (WP15): (also Innovation Manager)
ATOS (WP5)
B&B (WP16)
DTA (WP12)
JOT (WP11)

## Slide 18: Project Office (PO)
Infrastructure and resources to support the project management
It reports to the PCC
Responsible for
  Financial reporting, cost claiming and budgeting
  Management of intellectual property rights
  Management of knowledge dissemination
  Updating and consolidating work plans
  Providing support tools to the PCC
  Providing support tools for communication in the project
  Organisation of project meetings (logistics, agenda, minutes, and tasks to be completed after meetings)
The person in charge of project office is appointed by the PCO

## Slide 19: Advisory Board (AB)
AB has two workgroups
“Specialist workgroup”
  Experts in the fields of Big Data Analytics and Research
  It aims to evaluate the suitability, novelty, and soundness of the project results mainly from a theoretical point of view
“SME focus workgroup”
  Industry experts (mainly from SMEs)
  It aims to evaluate the impact and influence the project results could have from an industrial point of view, mainly evaluating the benefits for European SMEs
Advisory Board Chair (ABC)

## Slide 20: Advisory Board (AB)
Industry and academic experts in both workgroups are not directly involved in the technical activities
  They are related with organisations having significant technical expertise and/or business activities
This group will have to be consulted for the requirement elicitation
  Support the project to size the design to SME's needs

## Slide 21: Advisory Board (AB)
AB membership may be changed during the duration of the project when/if existing members cannot fulfill their role
The Advisory Board Chair (ABC) is elected by the PCC in the beginning of the project
The members of the Advisory Board will be invited
  To review project results
  Give feedback
The board meets annually
  Typically at the end of each year

## Slide 22: Advisory Board (AB)
TOREADOR consortium has already considered a potential constitution of AB workgroups
Some experts have been already invited to the AB and have accepted

## Slide 23: AB members
  ABC (AB chair):
    Rong Chang, IBM, US
  “Specialist workgroup” AB
  Will Van der Aalst, TUE, NL
  “SME focus workgroup” AB
  Massimo Banzi, Telecom, Italia
  Koij Zettsu, NICT, Japan
  Ron Claxton, British Telecom, UK

## Slide 24: Work Area Leader (WAL)
Work area leaders must
  Facilitate the communication among WPs
  Ensure early identification of problems (in cooperation with the STCO)

## Slide 25: Work Package Leader (WPL)
Work package leaders must
  Manage the individual work package
  Ensure that the results of their work packages are integrated into the overall project results (in cooperation with the STCO)
Other responsibilities of WPLs are
  Management of the technical and scientific activities of WPs
  Intra-package coordination
  Monitoring, assessment and reporting of the work conducted in the work package including any identified risks
    Reports should be directed to PCO and STCO
  Assurance of the quality of deliverables within the WP
  Compliance with the overall project quality plan

## Slide 26: Deliverables
85 deliverables
First deliverable: Quality Plan (M2)
Deliverable internal review process
  Two reviewers for each deliverable
  Revivers did not contribute to the deliverable
  See Quality Assurance WP in Work Area 5

## Slide 27: Communication
Internal communication strategy will be presented subsequently in the Project Quality Plan (delivered in M2)
Information exchange
  Working papers
  Project meetings
  Workshops
  Video and telephone conferences
E-mail will be the preferred means for sharing documents and know how
  Particularly sensitive information will be exchanged preferably by ordinary mail
Tools, file formats and configuration management used for project communication must be agreed upon at the kick off meeting

## Slide 28: Reporting
Reporting periods
  P1: from month 1 to month 12
  P2: from month 13 to month 24
  Final: from month 25 to the last month of the project
The Coordinator has to submit a consolidated report to the EC within 60 days after the end of each reporting period
The EC has to approve the costs claimed in the financial reports and transfer the corresponding payment within 105 days of their receipt to the Coordinator

## Slide 29: Reporting
Periodic reports shall include
  An overview, including a publishable summary, of the progress of work towards the objectives of the project, including achievements and attainment of any milestones and deliverables
  An explanation of the use of the resources
  A financial statement, from each beneficiary, together with a summary financial report consolidating the claimed contribution of the Union of all the beneficiaries in an aggregated form, based on the information provided in Form C by each beneficiary

## Slide 30: Reporting
Final report shall include
A final publishable summary report covering results, conclusions and socioeconomic impact of the project
A report covering the wider societal implications of the project,
  Including gender equality actions, ethical issues, efforts to involve other actors and spread awareness, as well as the plan for the use and dissemination of foreground

## Slide 31: Reimbursement of personnel costs
Conditions for reimbursement of personnel costs
Personnel must be directly hired by the beneficiary (the Organisation signing the EU contract)
Personnel must work under the sole technical supervision and responsibility of the beneficiary
The beneficiary may include in its personnel costs “permanent or temporary employees”, who have permanent or temporary working contracts
Personnel costs should reflect the total remuneration: salaries plus social security charges (but not extra costs as for example business bonus)

## Slide 32: Reimbursement of personnel costs
Only the hours worked on the project can be charged
Working time is the total number of hours worked, excluding holidays, personal time, sick leave, or other allowances
Working time to be charged must be recorded throughout the duration of the project by any reasonable means (e.g., timesheets)
  Employees have to record their time on a daily, weekly, or monthly basis using a paper or a computer-based system
  The timesheets have to be authorised and signed by the superior of the researcher or project manager

## Slide 33: Contact details
CINI
Address: Via Salaria, 113, Roma, Italy (00198)
Phone: +39 06 77274029 or +39 06 77274030
Skype:
Mail:

## Slide 34
Q&A